## BRD Use Case Status
UC ID | Use Case Name | Module | Priority | Backend Status | Frontend Status | Overall Status | Notes / Gaps
MODULE: USER AUTHENTICATION & REGISTRATION
UC-01 | Register New Student Account | Auth | Critical | ✅ | ✅ | ✅ | BE: Migration 0007 adds DOB/country/language/is_verified fields + email_verification_tokens. Register returns JWT tokens + verification token logged in dev. verify-email + resend endpoints exist. FE: LoginPage handles register mode, authStore manages tokens + user. Gap: No actual SMTP email sending (tokens logged to console only in dev).
UC-02 | Authenticate User (Login) | Auth | Critical | ✅ | ✅ | ✅ | BE: JWT access token (15min) + refresh token (7d). bcrypt password verification. FE: LoginPage + authStore.login() + automatic token refresh on 401.
UC-03 | Reset Forgotten Password | Auth | High | ✅ | ⚠️ | ⚠️ | BE: forgot-password + reset-password endpoints exist. Tokens expire in 1hr. FE: 'Forgot password?' link on LoginPage navigates to /login?forgot=true — no actual forgot/reset page implemented. Gap: No UI for password reset flow.
UC-04 | Link Parent to Student Account | Auth | High | ⚠️ | ⚠️ | ⚠️ | BE: ParentStudentLink model exists. Parent dashboard endpoints retrieve student data. FE: ParentDashboard lists students. Gap: No explicit linking-code generation/validation flow. No dedicated link/unlink endpoint. Parent sees first child only.
MODULE: STUDENT DASHBOARD
UC-05 | View Personalized Student Dashboard | Student | Critical | ✅ | ✅ | ✅ | BE: Enrollment + mastery + curriculum endpoints provide dashboard data. FE: StudentDashboard page with stats, learning path mini-view, quick actions. Gap: No streak counter or achievement badges displayed (gamification data not tracked).
MODULE: COURSE DISCOVERY & ENROLLMENT
UC-06 | Search & Browse Course Catalog | Discovery | High | ❌ | ❌ | ❌ | BE: No search/catalog endpoint exists. getCourses() has search param but no full-text search. FE: No course catalog page built. Gap: Major missing feature — no course browsing UI at all.
UC-07 | Enroll in a Course | Enrollment | Critical | ✅ | ✅ | ✅ | BE: Enrollment router (POST /enrollments, GET /enrollments). FE: StudentOnboarding auto-enrolls into first published course. Enrollment list on dashboard. Gap: No prerequisite validation before enrollment (student can enroll without meeting prerequisites).
MODULE: COURSE & CURRICULUM MANAGEMENT
UC-08 | Create New Course | Curriculum | Critical | ✅ | ⚠️ | ⚠️ | BE: Full CRUD for courses. FE: Admin/Teacher course creation form NOT built (only AssessmentManagement page exists for creation). Gap: No course creation UI for teachers.
UC-09 | Create Curriculum Hierarchy (Modules->Lessons->Concepts) | Curriculum | Critical | ✅ | ⚠️ | ⚠️ | BE: Full CRUD for modules, lessons, concepts, contents, exercises, examples, objectives. FE: Curriculum tree fetched and displayed (LearningPathPage, ProgressPage). Gap: No curriculum builder UI for teachers to create/edit the hierarchy.
UC-10 | Publish Course for Enrollment | Curriculum | High | ✅ | ❌ | ⚠️ | BE: Publish/unpublish endpoints exist for courses. FE: No UI for publishing courses. Gap: No publish button/flow in frontend.
MODULE: AI TUTOR
UC-11 | Start AI Tutor Session | AI Tutor | Critical | ✅ | ✅ | ✅ | BE: Teaching session endpoints (create, get, pause, end). LangGraph pipeline. FE: AITutorPage auto-starts session + auto-ends on unmount.
UC-12 | AI Adaptive Teaching Based on Student Response | AI Tutor | Critical | ✅ | ✅ | ✅ | BE: 7-node LangGraph pipeline (retrieve_memories -> teach -> ask_question -> evaluate_response -> diagnose -> provide_example/complete_concept). Gemini 1.5 Pro with mock fallback. FE: Chat interface sends student input via teach() endpoint.
UC-13 | End AI Tutor Session with Summary | AI Tutor | Critical | ✅ | ⚠️ | ⚠️ | BE: Session end/pause endpoints. FE: Session ends on unmount. Gap: No end-of-session summary displayed to student (BE likely returns data but FE doesn't show it).
MODULE: ASSESSMENT & MASTERY
UC-14 | Take Lesson Quiz / Assessment | Assessment | Critical | ✅ | ✅ | ✅ | BE: Full assessment CRUD, questions, attempts, auto-grading. FE: Full attempt flow (list -> detail -> attempt with timer -> submit -> results with review).
UC-15 | View Concept-by-Concept Mastery Progress | Assessment | High | ✅ | ✅ | ✅ | BE: Mastery router (overview, by concept, by course). FE: ProgressPage with mastery bar chart, areas to improve, strong areas.
MODULE: KNOWLEDGE GRAPH & LEARNING PATH
UC-16 | Maintain Knowledge Graph (Concepts & Prerequisites) | Knowledge Graph | High | ⚠️ | ❌ | ⚠️ | BE: Knowledge graph router (create edge, delete edge, get prerequisites). Gap: No UI for teachers to manage the knowledge graph. Admin-only access currently.
UC-17 | Generate Adaptive Learning Path | Knowledge Graph | High | ✅ | ✅ | ✅ | BE: Prerequisites from knowledge graph inform curriculum ordering. FE: LearningPathPage displays ordered lesson list with status.
MODULE: TEACHER DASHBOARD
UC-18 | View Course Analytics (Teacher) | Teacher | High | ✅ | ✅ | ✅ | BE: Teacher dashboard endpoints (students, progress, mastery, misconceptions, sessions, attempts, courses). FE: TeacherDashboard with stat cards + students list + recent sessions.
UC-19 | Identify & Support At-Risk Students | Teacher | Critical | ⚠️ | ⚠️ | ⚠️ | BE: Teacher can access individual student data (progress, mastery, misconceptions). FE: TeacherStudentDetail shows full student profile. Gap: No automated at-risk flagging (declining scores, engagement drops). No intervention tools (video upload, message). Teacher must manually identify struggling students.
UC-20 | Create & Monetize Courses | Teacher | High | ❌ | ❌ | ❌ | BE: No payment system, no revenue sharing, no payout processing. FE: No monetization UI. Gap: Entire payments/monetization module missing.
MODULE: PARENT DASHBOARD
UC-21 | View Child's Detailed Progress Report | Parent | Critical | ✅ | ✅ | ✅ | BE: 11 parent dashboard endpoints (students, progress, curriculum, mastery, misconceptions, sessions, activity, dashboard, reports). FE: ParentDashboard + ParentStudentDetail + ReportsPage + InsightsPage.
UC-22 | Configure Parental Controls (Time Limits, Sleep Mode) | Parent | High | ❌ | ❌ | ❌ | BE: No usage limit, break reminder, or sleep mode endpoints. FE: No parental controls UI. Gap: Entire safety/controls module missing.
UC-23 | Communicate with Teacher | Parent | Medium | ❌ | ❌ | ❌ | BE: No messaging/communication endpoints. FE: No messaging UI. Gap: Entire messaging module missing.
MODULE: ADMINISTRATOR
UC-24 | View Platform-Wide Analytics | Admin | High | ✅ | ✅ | ✅ | BE: Admin dashboard stats endpoint. Analytics overview + per-course analytics. FE: AdminDashboard + AnalyticsPage with system stats, per-course analysis.
UC-25 | Moderate User-Generated Content | Admin | High | ⚠️ | ⚠️ | ⚠️ | BE: Content ingestion draft/approve/publish flow exists. FE: AssessmentManagementPage for creating assessments. Gap: No content moderation queue UI. No community ratings. No automated quality checks.
MODULE: INSTITUTIONAL / SCHOOL DISTRICT
UC-26 | Onboard School District | Institutional | High | ❌ | ❌ | ❌ | Gap: Entire institutional module missing. No multi-tenant support, no district/school hierarchy, no bulk enrollment via CSV/SSO.
UC-27 | Generate Institutional Reports | Institutional | High | ❌ | ❌ | ❌ | Gap: No district-level analytics, no cross-school comparison reports, no auto-generated monthly reports for boards.
MODULE: GAMIFICATION & ACHIEVEMENT
UC-28 | Award Achievements & Badges | Gamification | Medium | ❌ | ❌ | ❌ | BE: current_streak_days on StudentProfile is the only gamification data point. Gap: No achievements system, no badges, no XP, no triggers.
UC-29 | Issue Certificate of Completion | Gamification | High | ❌ | ❌ | ❌ | Gap: No certificate generation (PDF), no verification URLs, no serial numbers.
MODULE: NOTIFICATION & COMMUNICATION
UC-30 | Send Progress Notification to Parent | Notifications | High | ❌ | ❌ | ❌ | BE: Email service logs to console only (stub). No real SMTP integration. No in-app notification system. FE: No notification UI. Gap: Entire notification engine missing in production.
MODULE: PAYMENT & MONETIZATION
UC-31 | Purchase a Course | Payments | High | ❌ | ❌ | ❌ | Gap: Entire payment module missing (no Stripe/PayPal, no checkout flow, no receipts).
UC-32 | Process Teacher Payouts | Payments | High | ❌ | ❌ | ❌ | Gap: No payout system, no earnings tracking, no revenue sharing.
MODULE: CONTENT INGESTION & UPLOAD
UC-33 | Upload & Parse Teaching Material (PDF/DOCX/TXT) | Content | Medium | ✅ | ❌ | ⚠️ | BE: Full content ingestion pipeline (upload, parse, draft CRUD, generate, approve, publish). Supports PDF/DOCX/TXT. FE: No upload UI built. Gap: Teachers cannot upload files via frontend.
MODULE: SAFETY, PRIVACY & PARENTAL CONTROLS
UC-34 | Enforce Usage Limits & Break Reminders | Safety | Critical | ❌ | ❌ | ❌ | Gap: No usage limits, no break reminders, no sleep mode enforcement. Entire safety module missing.
UC-35 | Enforce Data Privacy (COPPA/GDPR) | Safety | Critical | ⚠️ | ⚠️ | ⚠️ | BE: JWT auth, bcrypt passwords, CORS, security headers. Audit models exist. FE: None. Gap: No COPPA consent flow, no data export (GDPR right to access), no account deletion endpoint, no audit log writing.
MODULE: OFFLINE & ACCESSIBILITY
UC-36 | Download Lessons for Offline Use | Offline | Medium | ❌ | ❌ | ❌ | Gap: Entire offline mode missing. No content packaging/download, no offline sync.
TOTAL USE CASES
36 total use cases across 17 modules
✅ Fully Implemented: 12 (33%)
⚠️ Partially Implemented: 11 (30%)
❌ Not Implemented: 13 (36%)
Backend endpoints done: 18/36 | Frontend pages done: 12/36